## Sprint
Backlog Item | Task | Task Owner | Initial Estimate | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10
|  |  |  | 3/15-3/21 | 3/22-3/28 | 3/29-4/4 | 4/5-4/11 | 4/12-4/18 | 4/19-4/25 | 4/26-5/2 | 5/3-5/9 | 5/10-5/15 | 2021-05-15
|  |  |  | 239.5 | 212.9 | 186.3 | 159.7 | 133.1 | 106.5 | 79.9 | 53.3 | 26.7 | 0 | Ideal Burndown
|  |  | 275.5 | 239.5 | 223.5 | 187.5 | 181.5 | 170.5 | 153.5 | 115 | 94.5 | 41 | 0 | Remaining Hrs (Total)
|  |  | 275.5 | 52 | 36 | 6 | 11 | 17 | 38.5 | 20.5 | 53.5 | 41
Technology knowledge | frontend technology research | Xuan Shi | 8 | w1: 8
| frontend technology research | Jinfan Zhang | 8 | w1: 8
| frontend technology research | Cong Li | 8 | w1: 8
| backend technology research | Xuan Shi | 8 | w1: 8
| backend technology research | Jinfan Zhang | 8 | w1: 8
| backend technology research | Cong Li | 8 | w1: 8
| Compare frameworks of technologies | Jinfan Zhang, Cong Li, Xuan Shi | 4 | w1: 4
| Learn flask | Jinfan Zhang | 12 | w2: 12
| Learn flask | Cong Li | 12 | w2: 12
| Learn flask | Xuan Shi | 12 | w2: 12
System design | Determine project structure | Jinfan Zhang, Cong Li | 4 | w3: 4
| Create UI wireframe | Xuan Shi | 4 | w4: 4
| Create UI wireframe | Cong Li | 4 | w4: 4
| Create system architecture diagram | Xuan Shi | 6 | w5: 6
| Create system architecture diagram | Cong Li | 6 | w5: 6
| learn MySQL | Jinfan Zhang | 5 | w3: 2; w4: 3
| Try different approaches of DB | Jinfan Zhang | 5 | w5: 5
| Database structure | Jinfan Zhang | 3 | w6: 3
| Database structure | Cong Li | 3 | w6: 3
Login, sign up & home page | login Frontend | Xuan Shi | 4 | w6: 4
| login Frontend | Jinfan Zhang | 4 | w6: 4
| login backend | Jinfan Zhang | 2 | w6: 2
| Signup frontend | Xuan Shi | 2 | w6: 2
| Signup frontend | Jinfan Zhang | 2 | w6: 2
| Signup backend | Cong Li | 2 | w6: 2
| Signup backend | Jinfan Zhang | 3 | w6: 3
| User information section frontend | Jinfan Zhang | 2 | w6: 2
| User information section backend | Jinfan Zhang | 2 | w6: 2
| Admin section frontend | Cong Li | 3 | w6: 3
| Admin section frontend | Jinfan Zhang | 3 | w6: 3
| Admin section backend | Jinfan Zhang | 3.5 | w6: 3.5
| Home page frontend | Jinfan Zhang | 6 | w9: 6
| Home page frontend | Cong Li | 3 | w9: 3
| Home page backend | Jinfan Zhang | 2 | w9: 2
Open and close accounts | Open accounts frontend | Cong Li | 3.5 | w7: 3.5
| Open accounts frontend | Jinfan Zhang | 3 | w7: 3
| Open accounts backend | Jinfan Zhang | 5 | w7: 5
| Close existing accounts frontend | Jinfan Zhang | 2 | w7: 2
| Close existing accounts frontend | Xuan Shi | 2 | w7: 2
| Close existing accounts backend | Jinfan Zhang | 5 | w7: 5
Transfer | Internal transfer frontend | Cong Li | 2.5 | w8: 2.5
| Internal transfer frontend | Jinfan Zhang | 2 | w8: 2
| internal transfer backend | Jinfan Zhang | 3.5 | w8: 3.5
| Wire transfer frontend | Jinfan Zhang | 2 | w8: 2
| Wire transfer frontend | Cong Li | 3 | w8: 3
| Wire transfer frontend | Xuan Shi | 2.5 | w8: 2.5
| Wire transfer backend | Jinfan Zhang | 4 | w8: 4
| Wire transfer backend | Cong Li | 2 | w8: 2
| Recurring transection frontend | Jinfan Zhang | 2 | w9: 2
| Recurring transection frontend | Xuan Shi | 2 | w9: 2
| Recurring transection backend | Jinfan Zhang | 8 | w9: 8
| Transaction history view frontend | Jinfan Zhang | 2 | w8: 2
| Transaction history view frontend | Xuan Shi | 3.5 | w8: 3.5
| Transaction history view frontend | Cong Li | 3.5 | w8: 3.5
| Transaction history view backend | Jinfan Zhang | 3.5 | w8: 3.5
| view transaction up to 18 months frontend | Jinfan Zhang | 2 | w8: 2
| view transaction up to 18 months backend | Jinfan Zhang | 4 | w8: 4
| view transaction up to 18 months frontend | Xuan Shi | 2 | w8: 2
| Search transaction frontend | Jinfan Zhang | 4 | w8: 4
| Search transaction backend | Jinfan Zhang | 4 | w8: 4
| Search transaction backend | Xuan Shi | 3.5 | w8: 3.5
Optimization & deploy | Jsonfy input & output API | Cong Li | 6 | w9: 6
| Deploy API to AWS | Cong Li | 2 | w9: 2
| Deploy API to AWS | Jinfan Zhang | 2 | w9: 2
| Deploy API to AWS | Xuan Shi | 2 | w9: 2
| Code refactoring | Jinfan Zhang | 3 | w9: 3
| Code refactoring | Cong Li | 3 | w9: 3